## Current
[6 empty] | Johnstown Planning & Development Department Current Development Review List (2-25-21) For project information contact: planning@townofjohnstown.com 970-587-4664 |  |  |  |  | KM = Kim Meyer DW = Darryll Wolnik KC = Kristin Cote
Project File # | Project Name | Project Type | Status | Address | Parcel Number(s) | Submittal Year | Project Description | Use Type | Acres | Lots | Units | PLANNER | Contact Name | Contact Business Name | Contact Phone # | Contact Address | Contact Email | 1st Submittal Date | Last Submittal | Due Date | # of Days Since Last Submittal | Total # of Submittals | Development Agreement | PC date | TC date | Approval / Denial date | Resolution / Ordinance Date | Res / ORD # | WSSA
ANX20-0002 | Graybill Annexation | Annexation | Recommended by PZC | 2190 SE Frontage Rd | 8527000002 | 2020 | Single Property Annexation |  | 48.597 |  |  | KM/KC
ANX20-0003 | WCR50-LCR14 | Annexation | Hearings | Not assigned |  | 2020 | Road Right of Way Annexation | Road |  | 0 |  | KM/DW
ANX20-0004 | North Ridge | Annexation | 1st Review Returned | Pt of NW 1/4 of SE 1/4, Section 22, Twp 5N, Range 68W | 8522000005 | 2020 | Retail/Flex Developement | Retail/Commercial/ Residential (FLEX) | 36.97 |  |  | DW
PDP20-0001 | I-25 Gateway Center | Prelim Development Plan | 1st Review Returned | L1-4, 7 & 8, B3 | Multiple | 2020 | Retail/Flex development | Office |  | 0 |  | DW
PUD20-0003 | The Ridge Design Guidelines (The Villages) | Amedment to the Performance Standards | 1st Review Underway | The Ridge at Johnstown properties | Multiple | 2020 | Mixed use development | Mixed Use |  | 0 |  | KM
PUD20-0002 | Keto-Maplewood PUD | Planned Unit Development | 3rd Review Underway | 22211 COUNTY ROAD 15 | 105907000022, 105907300044, 105907300043 | 2020 | PUD Development | Single Family Residential Lots | 275 |  | 950 | DW
SDP20-0011 | Iron Horse Spec Buildings | Site Plan | SPD Approved - Awaiting WSSA | Lt 2, Iron Horse Filing 2 | 8513210002 | 2020 | Industrial/Flex Building | Industrial | 2.004 |  |  | KC
SDP20-0012 | Parish & 60 Gas Station | Site Plan | 3rd Review Underway | 106 E S 1ST ST | 105909203014 | 2020 | Gas Station | Commercial | 0.373 |  |  | DW
SDP20-0013 | Trade at 2534 | Site Plan | 1st Review Underway | Lt 4, Blk 7, 2534 Filing 9 | 8514119004 | 2020 | Industrial/Flex Buildings | Commercial | 16.76 |  |  | DW
SDP20-0014 | Slim Chickens | Site Plan | 1st Review completed | Lts 4 & 5, Blk 2 2534 Filing No 21 | 8515132004 and 8515132905 | 2020 | Fast Food Restaurant | Commercial | 1 |  |  | KC
SDP21-0001 | 4615 Venture Drive - Lanting Bldg | Site Plan | 1st Review Underway | Lot 16, Block 10 2534 Filing No 6 | 8514215016 | 2021 | Industrial/Flex Buildings | Commercial | 1.63 |  |  | KC
SDP21-0002 | Crowne at 2534 Filing 12 & 15 | Site Plan | 1st Review Submitted | Lts 1 & 4 2534 Filing No 12 | 8514124001 and 8514123004 | 2021 | Multi Family Residential | Multi Family Residential | 11.79 |  |  | DW/KC
SDP20-0009 | Iron Wood Shops Modification | Site Plan | 2nd Review Returned | 4840 LARIMER PKWY | 8514237001 | 2020 | Drive Thru Addition | Commercial | 2.37 |  |  | DW
SUB19-0006 | The Ridge (Filing 2) | Subdivision | Ready for hearings | 2051 S LCR 3E | 8526200003 | 2019 | SFR | Residential |  | 81 |  | DW
SUB20-0002 | Welty Ridge Preliminary Subdivision | Subdivision | HOLD 1st Review Returned | 3466 WCR 48 | 106110000026 | 2020 | Prelim Plat | Mixed Use |  | 7 |  | DW
SUB20-0011 | TRR 7 Amendment 1 | Subdivision | 2nd Review Underway | not assigned |  | 2020 | Replat | Residential |  | 5 |  | KM
SUB20-0005 | Thompson River Ranch Filing 8 | Subdivision | Reviews Complete - Awaiting PC & TC | River Ranch Pkwy & High Plains Blvd | 8523100001 | 2020 | 47-lot detached single-family subdivision | Residential |  | 47 |  | DW
SUB20-0007 | TRR 12 | Subdivision | 2nd Review Returned | Not assigned | 8523100001, 8523000010, 8523111002 | 2020 | Replat | Commercial/Industrial | 28 | 164 |  | DW
SUB20-0010 | TRR 13 | Subdivision | 1st Review Underway | Not assigned | 8524000013 | 2020 | Residential Plat | Residential | 81.362 | 254 |  | DW
SUB20-0009 | Replat of Lot 44 Country Acres 9 | Subdivision | Review Underway | 1106 SANDRA DR | 105908211044 | 2020 | Replat | Detention Access & Utility easement | .317 Acres |  |  | KM
SUB20-00013 | Paulter Farms Estates | Subdivision | 1st Review Underway | Not assigned | 105920444001 | 2020 | Residential Plat | Residential | 11.119 | 11 |  | DW
SUB20-0014 | TRR 15 | Subdivision | 1st Review Underway | 7331 E COUNTY ROAD 18 | 8523100001 and 8523000010 | 2020 | Replat | Residential | 29.337 | 166 |  | DW
SUB20-0015 | The Granary | Subdivision | 1st Review Underway | 22211 COUNTY ROAD 15 | 105907000022, 105907300044, 105907300043 | 2020 | Residential Plat | Residential | 294.76 | 921 |  | DW
SUB20-0017 | 2534 Filing No. 23 - Slim Chickens | Subdivision | 1st Review Complete | Lts 4 & 5, Blk 2 2534 Filing No 21 | 8515132004 and 8515132905 | 2020 | Simple Re-plat | Commercial | 1 |  |  | kc
SUB20-0016 | Mountain View West 1st Replat | Subdivision | 2nd Review Underway | Not assigned | 105909208001 | 2020 | Residential Plat | Residental | 17.29 | 143 |  | DW
SUB20-0008 | Revere (Great Plains Village) Filing 1 | Subdivision | 3rd Review Returned | Not assigned | 106102000001, 10210200001, 106102200030, 106102000019 | 2020 | Residential Plat | Residential | 73.578 | 320 |  | DW |  | Forestar
SUB21-0002 | Replat of Amended JT Heights 3rd | Subdivision | 1st Review Underway | Multiple | Multiple | 2021 | Residential Plat | Residential |  | 8
SUB21-0003 | Crowne at 2534 Filing 12 & 15 | Subdivision | 1st Submittal Received | Lts 1 & 4 2534 Filing No 12 | 8514124001 and 8514123004 | 2021 | 2021 | Multi Family Residential | 11.79 | 1 |  | DW/KC
USR19-001 | Oakwood OG | USR | 2nd Review Returned - Partial 3rd submittal | 1000 S LCR 3E | 8524000013 | 2019 | 14 Wells, 1 Pad | Oil & Gas Extraction |  |  |  | KM
USR19-002 | Point Three OG | USR | 5th Review Underway | 1700 WCR 17 | 105916300047 | 2019 | 16 Wells, 1 Pad | Oil & Gas Extraction |  |  |  | KM
USR19-003 | Shake and Bake OG | USR | 5th Review Complete | 22764 FRONTAGE RD | 106111000001 | 2019 | 23 Wells, 1 Pad | Oil & Gas Extraction |  |  |  | KM
USR20-0001 | Fall River Monopine | Site Plan | Rec Denial @ PZC Submittal 2 Review Underway 11/30/20 | 5360 Ronald Reagan Blvd | 8515125001 | 2020 | 70-foot Monopine | Wireless Communication
ZON20-0003 | The Ridge ODP Amendment | PUD Amendment | pre-app |  |  | 2020
ZON20-0004 | Graybill Zoning | Establish Zoning | Recommended by PZC | 2190 SE Frontage Rd | 8527000002 | 2020 | Zoning of annexed land |  | 48.597 |  |  | KM
WCF20-0001 | SQL Small Cell | WCF | pre-app |  |  | 2020 | 6 Small Cell WCF in ROW, Downtown | Wireless Communication |  |  |  | KM

## Completed
Johnstown Planning & Development Department Completed Development Review List (9-30-20) | [8 empty] | KM = Kim Meyer DW = Darryll Wolnik KC = Kristin Cote
Project File # | Project Name | Project Type | Status | Address | Parcel Number | Submittal Year | Project Description | Use Type | Acres | Lots | Units | PLANNER | Contact Name | Contact Business Name | Contact Phone # | Contact Address | Contact Email | 1st Submittal Date | Last Submittal | Due Date | Total # of Submittals | Development Agreement | PC date | TC date | Approval / Denial date | Resolution / Ordinance Date | Res / ORD # | WSSA
PUD19-004 | I-25 Gateway 2nd Amendment |  | Final Complete |  |  | 2019 | Commercial / Industrial PUD |  |  |  |  | KM | [9 empty] | na | 2019-06-12 | 7/1/19; 7/15/19 | 2019-06-12 | 2019-07-15 |  | na
PUD19-005 | Mountain View West Sports Lighting |  | Final Complete |  |  | 2019 | Recreation
SDP19-001 | Bonaventure |  | Approved |  |  | 2019 | Senior Housing
SDP19-002 | Red Barn Liquor |  | Approved - Under Construction | 50 Gateway Cr |  | 2019 | Commercial
SDP19-004 | Hobby Lobby |  | Approved - Under Construction | 4905 Thompson Pkwy |  | 2019 | Retail
SDP19-005 | Firestone |  | Final Complete | 4840 Larimer Pkwy. |  | 2019 | Commercial
SUB19-003 | 2534 Filing 4 Amd |  | Final Complete | 4860-4880 Larimer Pkwy. |  | 2019 | Commercial
VAR19-001 | 3137 Dunbar Way Variance |  | Final Complete | 3137 Dunbar Way | 106101416022 | 2019 | side setback variance for SFD |  |  |  |  | KM | Bruce Gillam
VAR19-002 | 3030 Dunbar Way Variance |  | Final Complete | 3130 Dunbar Way | 106101407013 | 2019 | side setback variance for SFD |  |  |  |  | KM | Bruce Gillam
SDP19-008 | Ironwood Shops |  | Approved - Under Construction | 4830 Larimer Pkwy. |  | 2015 | Commercial
SDP19-007 | Johnstown Plaza Apartments |  | Approved - Awaiting Construction | 5150 Ronald Regan Blvd. |  | 2019 | MFR
SUB19-005 | Lot 8, Blk 10, 2534 Flg 6 Amd | Minor Subdivision | Approved | 4513 Endeavor Dr. | 8514215008 | 2019 | Commercial
| Johnstown Village F 1 | PUD | Approved |  |  | 2018 | Residential | [6 empty] | Not signed | 2018-09-12 | 2019-09-04 | 2019-09-04 | 2019-09-04 | 2019-18
PUD19-001 | Great Plains Village | ODP | Approved |  |  | 2019 | Mixed-Use PUD | [15 empty] | 2019-12-11 | 2020-01-06 | 2020-01-06
PUD19-003 | Welty Ridge | ODP | Approved |  |  | 2019 | Mixed-Use PUD | [15 empty] | 2019-12-11 | 2020-01-06 | 2020-01-06
SDP19-006 | Canyon Bakehouse Amendment | Site Plan | Approved - Under Construction | 3600 Ronald Regan Blvd. |  | 2019 | Industrial | Industrial |  |  |  | KM
SUB19-001 | The Ridge (Filing 1) | Subdivision | Approved - Under Construction | 2000 S LCR 3E | 8526100005 | 2019 | SFR | Residential |  |  |  | DW
SUB19-002 | Johnstown Heights Amended | Subdivision | 2nd Redlines Returned | 1150 N 2nd St |  | 2019 | SFR | Residential |  |  |  | KM
SUB19-008 | TRR 10 | Subdivision | Approved - Under Construction |  | 8523111001, 8523111002 | 2019 | Residential |  | 40 |  | KM | Todd Bloom | [9 empty] | draft | 2018-01-24 | 2019-12-16 | 2019-12-16 | 2019-12-16 | 2019-30 | draft
SUB19-008 | TRR 10 | FDP | Approved |  | 8523111001, 8523111002 | 2019 | Residential |  | 40 |  | KM | [6 empty] | 2019-11-21
SUB19-010 | Johnstown Farms F 3 | Subdivision | Approved |  | 105909000020 | 2018 | Residential |  | 241 |  | KM | [11 empty] | 2019-01-30 | 2019-11-18 | 2019-12-02 | 2019-12-02 | 2019-26
SUB19-010 | Johnstown Farms F 3 | FDP | Approved |  | 105909000020 | 2018 | Residential |  | 241 |  | KM | [11 empty] | 2019-01-30 | 2019-11-18 | 2019-12-02 | 2019-12-02 | 2019-26
SDP20-0005 | AC Ice | Site Plan | Approved | L1, B2 Gateway #4 | 106103427001 | 2020 | Warehouse | Industrial |  |  |  | DW
| Johnstown Village | Subdivision | Under Construction |  | 105907200005 | 2017 | Residential |  | 263 |  | KM | [11 empty] | 2018-09-12 | 2019-08-19 | 2019-09-04 | 2019-09-04 | 2019-18
| Johnstown Village | FDP | Under Construction |  | 105907200005 | 2017 | Residential |  | 263 |  | KM | [11 empty] | 2018-09-12 | 2019-09-04 | 2019-09-04 | 2019-09-04 | 2019-164
SUB19-011 | TRR 11, 1st Amd | Subdivision | Approved |  | 8523116002 | 2019 | Institutional |  | 1 |  | DW | [10 empty] | N/A | N/A | N/A |  | N/A | N/A
SUB20-0004 | Corbett Glen 4 Amended - Replat | Subdivision | Signed and Recorded |  | 106101418002, 106101418003, 106101418004 | 2020 | Residential |  | 3 |  | DW | [10 empty] | NA | NA | NA | NA | NA | NA | NA
SDP20-001 | Liberty Lot 5 | Site Plan | Approved | 4867 Venture Dr | 8514229005 | 2020 | Office Flex
SDP20-0003 | 2534 Retail Paint Store | Wireless | Approved - Under Construction | 4870 Larimer Pkwy | 8514233002 | 2020 | Retail Commercial
ZON20-0001 | I-25 Gateway PUD Amendment | PUD Amendment | Approved |  |  | 2020 | Industrial Flex | [15 empty] | 2020-05-13
SDP19-0007 | Johnstown Plaza Apartments | Site Plan | Approved - Under Construction | 5150 Ronald Reagan Blvd | 8515128001 | 1999 | Residential | 11.6 |  | 252 | PLN
SDP19-0012 | At Home | Site Plan | Approved - Under Construction | 4905 Thompson Pkwy | 8515133004 | 2019 | Retail Commercial
ANX19-01 | Ridge Annexation | Annexation | Completed | 6604 E LCR 18 | 8523000013 | 2019 |  | 9.6 |  |  | DW
USR19-0004 | Cito O&G USR Amendment | USR Amendment | Admin Approval | 5050 Weld County Rd 50 | 106101200045 | 2020 | Extraction | 54.2 |  |  | DW
SDP20-0001 | Liberty Lot 5 | Site Plan | Approved | 4853 Venture Drive | 8514229005 | 2020 | Office | 1.93 |  |  | DW
SDP20-0004 | McDonalds Façade Project | Site Plan | Admin Approved | 150 PARISH AVE JOHNSTOWN | 105908120008 | 2018 | Commercial |  |  |  | DW
SDP20-0006 | Liberty Lot 3 | Site Plan | Approved | 4872 Endeavor Drive | 8514238000 | 2020 | Commercial |  |  |  | KC
SUB19-009 | TRR 7 | Subdivision | Approved |  | 8523100001 | 2015 |  | 47 |  | DW | [11 empty] | 2015-02-25
SUB19-009 | TRR 7 | FDP | Apprvoed |  | 8523100001 | 2019 |  | 47 |  | DW
SUB20-0001 | Iron Horse Filing 2 Lot 1 Amd | Subdivision | Complete |  | 8513208001 | 2020 |  | 3 |  | DW
USR20-0002 | CUG 301 W S 1st St | Conditional Use | Approved | 301 W S 1st Street | 105905423006 | 2020 | Residential in CB zone | Residential
USR20-0003 | CUG 305 W S 1st St | Conditional Use | Approved | 305 W S 1st Street | 105905423007 | 2020 | Residential in CB zone | Residential
SUB21-0001 | RePlat of Lot 16, County Acres Subdivision Eighth Filing | Subdivision | Approved - Awaiting Mylars | 1112 and 1114 County Acres Court | 105908210016 | 2021 | Simple Replat | Residential |  | KC | KC
SDP20-0007 | Atlas Self Storage | Site Plan | Approved - Pending permits and water acquistion | 3787 RONALD REAGAN BLVD | 8513210001 | 2020 | RV Storage Unit | Commercial | 2.16 |  |  | KC
ANX20-0001 | Podtburg Annexation | Annexation | Approved by TC 11/16/20 | 5651 WCR 42 | 106124000007, 106124000008, 106124000009, 106124200001, 106113000010 | 2020 | Serial Annexation by Owner |  | 448 |  |  | DW
ZON20-0002 | Podtburg Annexation Zoning | Establish Zoning | Approved by TC 11/16/20 | 5651 WCR 42 | 106124000007, 106124000008, 106124000009, 106124200001, 106113000010 | 2020 | Establish Zoning for Podtburg Annexation | Residential | 448

## Historical
Project File # | Project Name | Project Type | Status | Address | Parcel Number | Submittal Year | Use Type | Acres | Lots | Units | Contact Name | Contact Business Name | Contact Phone # | Contact Address | Contact Email | Development Agreement | PC date | TC date | Approval / Denial date | Resolution / Ordinance Date | Res / ORD # | WSSA
| Johnstown Farms 1 | Subdivision | Weld
| Johnstown Farms 1 Amd 1 | Subdivision | Weld
| Johnstown Farms 1 Amd 2 | Subdivision | Weld
| Johnstown Farms 1 Amd 3 | Subdivision | Weld
| Johnstown Farms 1 Amd 4 | Subdivision | Weld
| Rocksbury Ridge 1 | Subdivision | Weld
| Rocksbury Ridge 1 LL Adj | Subdivision | Weld
| Rocksbury Ridge 2 Corr | Subdivision | Weld
| Rocksbury Ridge 2 Rplt | Subdivision | Weld
| Faith Lutheran Church 1 | Subdivision | Weld
| Carlson Farms 1 | Subdivision | Weld
| Carlson Farms 2 | Subdivision | Weld
| Carlson Farms LL Adj Lots 9&10 Blk 4 | Subdivision | Weld
| Carlson Farms LL Adj 1 | Subdivision | Weld
| Carlson Farms LL Adj 2 | Subdivision | Weld
| Carlson Farms LL Adj 3 | Subdivision | Weld
| Corbett Glen 1 | Subdivision | Weld
| Corbett Glen 2 | Subdivision | Weld
| Corbett Glen 3 | Subdivision | Weld
| Corbett Glen 4 | Subdivision | Weld
| Corbett Glen 4 Amd | Subdivision | Weld
| Corbett Glen 4 Amd Tract D | Subdivision | Weld
| Clearview 1 | Subdivision | Weld
| Clearview 2 | Subdivision | Weld
| Clearview 3 | Subdivision | Weld
| Clearview 4 | Subdivision | Weld
| Clearview 5 | Subdivision | Weld
| Clearview Minor | Subdivision | Weld
| Podtburg Village | Subdivision | Weld
| Rolling Hills Ranch 1 | Subdivision | Weld
| Rolling Hills Ranch 2 | Subdivision | Weld
| Rolling Hills Ranch 3 | Subdivision | Weld
| Rolling Hills Ranch 3 Amd Lots 7-12 | Subdivision | Weld
| Rolling Hills Ranch 4 | Subdivision | Weld
| Rolling Hills Ranch 5 | Subdivision | Weld
| Rolling Hills Ranch 6 | Subdivision | Weld
| Rolling Hills Ranch 7 | Subdivision | Weld
| Rolling Hills Ranch 8 | Subdivision | Weld
| Rolling Hills Ranch 9 | Subdivision | Weld
| Rolling Hills Ranch 10 | Subdivision | Weld
| Rolling Hills Ranch 11 | Subdivision | Weld
| Rolling Hills Ranch 12 | Subdivision | Weld
| Rolling Hills Ranch 13 | Subdivision | Weld
| Rolling Hills Ranch 13 Amd Lots 41-42 | Subdivision | Weld
| Rolling Hills Ranch 13 4th Amd Lots 10-13 & 21-23 | Subdivision | Weld
| Rolling Hills Ranch 14 | Subdivision | Weld
| Rolling Hills Ranch 14 LLA | Subdivision | Weld
| Rolling Hills Ranch 15 | Subdivision | Weld
| Sunrise Ridge | Subdivision | Weld
| Sunrise Ridge Amd Lots 16-17 | Subdivision | Weld
| Redstone Hills | Subdivision | Weld
| Callahan Heights | Subdivision | Weld
| Callahan Heights 1st Add | Subdivision | Weld
| Grays | Subdivision | Weld
| Lieser | Subdivision | Weld
| Johnstown Heights 1 | Subdivision | Weld
| Johnstown Heights 2 | Subdivision | Weld
| Johnstown Heights 3 | Subdivision | Weld
| Johnstown Heights 3 Amd | Subdivision | Weld
| Knolls 1 | Subdivision | Weld
| Knolls 1 Rplt L1 B2 | Subdivision | Weld
| Knolls 1 Rplt L2 B2 | Subdivision | Weld
| Knolls 1 Rplt L3 B2 | Subdivision | Weld
| Knolls 1 Rplt L4 B2 | Subdivision | Weld
| Knolls 1 Rplt L5 B2 | Subdivision | Weld
| Knolls 2 | Subdivision | Weld
| Knolls 2 Rplt L5 B2 | Subdivision | Weld
| Knolls 2 Rplt L4 B2 | Subdivision | Weld
| Knolls 2 Rplt L3 B2 | Subdivision | Weld
| Knolls 2 Rplt L2 B2 | Subdivision | Weld
| Knolls 2 Rplt L1 B2 | Subdivision | Weld
| Knolls 2 Rplt L1 B1 | Subdivision | Weld
| Knolls 2 Rplt L2 B1 | Subdivision | Weld
| Knolls 2 Rplt L3 B1 | Subdivision | Weld
| Knolls 2 Rplt L4 B1 | Subdivision | Weld
| Knolls 3 | Subdivision | Weld
| Knolls 3 Rplt L6 B3 | Subdivision | Weld
| Knolls 3 Rplt L12 B2 | Subdivision | Weld
| Knolls 3 Rplt L6 B2 | Subdivision | Weld
| Knolls 3 Rplt L4 B1 | Subdivision | Weld
| Knolls 3 Rplt L5 B1 | Subdivision | Weld
| Knolls 3 Rplt L6 B1 | Subdivision | Weld
| Mary C Parish | Subdivision | Weld
| Mary C Parish Rplt Lots 2-4 | Subdivision | Weld
| Mary C Parish 2 | Subdivision | Weld
| Parish Heights | Subdivision | Weld
| Parish Heights 1st Add | Subdivision | Weld
| Parish Heights 2nd Add | Subdivision | Weld
| Johnstown Square 1 | Subdivision | Weld
| Johnstown Square 2 | Subdivision | Weld
| Johnstown Square 3 | Subdivision | Weld
| Johnstown (Original Plat) | Subdivision | Weld
| Johnstown Rplt B4 | Subdivision | Weld
| Qwest Rplt | Subdivision | Weld
| Great Western | Subdivision | Weld
| Great Western Amd Lots 19-21 | Subdivision | Weld
| Huwa Commercial Condo | Subdivision | Weld
| Public Works Facility | Subdivision | Weld
| Johnstown Industrial Park | Subdivision | Weld
| Johnstown Industrial Park Rplt L1 | Subdivision | Weld
| Johnstown Industrial Park Rplt L2 | Subdivision | Weld
| Johnstown Industrial Park Rplt L3-4 | Subdivision | Weld
| Purvis | Subdivision | Weld
| Johnstown Colony | Subdivision | Weld
| Mountain View West | Subdivision | Weld
| Castle Pines Professional Condos | Subdivision | Weld
| Johnstown Center 1 | Subdivision | Weld
| Johnstown Center 1 Commercial Amd | Subdivision | Weld
| Johnstown Center 1 Amd Rplt Lots 3 & 6 | Subdivision | Weld
| Johnstown Center 1 Amd Rplt Lots 3 & 6 LLA | Subdivision | Weld
| Johnstown Center 2 | Subdivision | Weld
| Johnstown Center 3 | Subdivision | Weld
| Johnstown Center 4 | Subdivision | Weld
| Mohawk | Subdivision | Weld
| Country Acres 1 | Subdivision | Weld
| Country Acres 1 Rplt B1 L 10-17 Vacation and Rededication | Subdivision | Weld
| Country Acres 1 Rplt LA B2 | Subdivision | Weld
| Country Acres 2 | Subdivision | Weld
| Country Acres 3 | Subdivision | Weld
| Country Acres 4 | Subdivision | Weld
| Country Acres 5 | Subdivision | Weld
| Country Acres 5 Rplt L 24 | Subdivision | Weld
| Country Acres 5 Rplt L 23 | Subdivision | Weld
| Country Acres 5 Rplt L21-22 | Subdivision | Weld
| Country Acres 6 | Subdivision | Weld
| Country Acres 7 | Subdivision | Weld
| Country Acres 8 | Subdivision | Weld
| Country Acres 8 Rplt L23 | Subdivision | Weld
| Country Acres 8 Rplt L21 | Subdivision | Weld
| Country Acres 8 Rplt L20 | Subdivision | Weld
| Country Acres 8 Rplt L19 | Subdivision | Weld
| Country Acres 9 | Subdivision | Weld
| Country Acres 9 Rplt 1 | Subdivision | Weld
| Cottonwood Court 1 | Subdivision | Weld
| Stroh Farm 1 | Subdivision | Weld
| Stroh Farm 1 LLA | Subdivision | Weld
| Stroh Farm 2 | Subdivision | Weld
| Stroh Farm 2 LLA | Subdivision | Weld
| Stroh Farm 3 | Subdivision | Weld
| Stroh Farm 4 | Subdivision | Weld
| Stroh Farm 5 | Subdivision | Weld
| Stroh Farm 6 | Subdivision | Weld
| Stroh Farm 7 | Subdivision | Weld
| Grays Farm | Subdivision | Weld
| I-25 Gateway Center 2 Rplt A | Subdivision | Weld
| I-25 Gateway Center 2 Rplt A Amd | Subdivision | Weld
| I-25 Gateway Center 3 Rplt A | Subdivision | Weld
| Mountain View Commerical Park Condo | Subdivision | Weld
| Mountain View Commercial Park Units A-H | Subdivision | Weld
| I-25 Gateway Center 5 | Subdivision | Weld
| Five Star Business Park 3 | Subdivision | Weld
| Five Star Business Park Condos 2 | Subdivision | Weld
| Five Star Business Park Condos | Subdivision | Weld
| I-25 Gateway Center 4 | Subdivision | Weld
| I-25 Gateway Center 4 Rplt L5&6 B3 | Subdivision | Weld
| I-25 Gateway Center 4 Rplt B | Subdivision | Weld
| I-25 Gateway Center 6 | Subdivision | Weld
| Basher Drive Condo | Subdivision | Weld
| Thompson River Ranch 1 | Subdivision | Larimer
| Thompson River Ranch 1 Amd 1 | Subdivision | Larimer
| Thompson River Ranch 1 Minor Resub | Subdivision | Larimer
| Thompson River Ranch 2 | Subdivision | Larimer
| Thompson River Ranch 3 | Subdivision | Larimer
| Thompson River Ranch 4 | Subdivision | Larimer
| Thompson River Ranch 4 Amd 1 | Subdivision | Larimer
| Thompson River Ranch 5 | Subdivision | Larimer
| Thompson River Ranch 6 | Subdivision | Larimer
| Thompson River Ranch 7 | Subdivision | Larimer
| Thompson River Ranch 8 | Subdivision | Larimer
| Thompson River Ranch 9 | Subdivision | Larimer
| Thompson River Ranch 9 Amd 1 | Subdivision | Larimer
| Thompson River Ranch 11 Amd 1 | Subdivision | Larimer
| TRR 9 | Subdivision | Recorded - Under Construction | [6 empty] | Residential | [14 empty] | 2018-05-07 |  | 2018-06-04 | 2018-08 | 2018-05-07
| TRR 9 | FDP | Approved | [6 empty] | Residential
| TRR 6 | Subdivision | [7 empty] | Residential | [12 empty] | Yes | 2015-02-25 | 2017-02-22 | 2017-02-22 | 2017-05-01 | 2017-08A
| TRR 6 | FDP | [7 empty] | Residential
| TRR 5 | Subdivision | COMPLETE | [6 empty] | Residential | [12 empty] | Yes | 2014-04-23 | 2015-05-04 | 2015-05-04 | 2015-05-04 | 2015-04
| TRR 5 | FDP | ? | [6 empty] | Residential
| TRR 4 | Subdivision | COMPLETE | [6 empty] | Residential
| TRR 4 | FDP | [7 empty] | Residential | [12 empty] | Yes | 2014-01-08 | 2014-03-17 | 2014-03-17 | 2014-09-03 | 2014-09
| TRR 2 | Subdivision | COMPLETE | [6 empty] | Residential
| TRR 1-4 | FDP | COMPLETE | [6 empty] | Residential
| TRR 1 | Subdivision | COMPLETE | [6 empty] | Residential | [12 empty] | Yes | 2005-05-11 | 2005-07-06 | 2005-07-06 | 2005-07-18 | 2005-23

## Dead
Project File # | Project Name | Project Type | Status | Address | Parcel Number(s) | Submittal Year | Project Description | Use Type | Acres | Lots | Units | PLANNER | Contact Name | Contact Business Name | Contact Phone # | Contact Address | Contact Email | 1st Submittal Date | Last Submittal | Due Date | # of Days Since Last Submittal | Total # of Submittals | Development Agreement | PC date | TC date | Approval / Denial date | Resolution / Ordinance Date | Res / ORD # | WSSA
?SDP19-004? | Primrose School |  | WITHDRAWN |  |  | 2019 | School
SDP19-003 | McDonald's (S. Parish) |  | Approved - Incomplete, On Hold | 150 S. Parish Ave. |  | 2017 | Restaurant
PUD19-002 | Great Plains Village North |  | Combined into PUD19-001 |  |  | 2019 | Commercial PUD / Park of GPV
SUB19-004 | 2nd Rptl, Lot 1 Johnstown Industrial Park | Subdivision | On Hold | 1 Industrial Park Ct. | 105904306001 | 2019 | Industrial | Industrial |  |  |  | KM
| Riverbend Estates 1 | PUD | Approved / Expired |  |  |  | Residential
| Ridgeview Ranch | PUD | PZC Approval Expired? |  |  |  | Residential | [15 empty] | 2018-11-14

## Housing Starts Est
|  | TOTAL |  |  | 2021 |  |  | 2022 |  |  | 2023 |  |  | 2024 |  |  | 2025 |  |  | 2026 |  |  | 2027 |  |  | 2028 |  |  | 2029 |  |  | 2030
Project Name - Estimates Housing Starts *significant assumptions (economy, pace of sales, dev/builder capacity) are used to create this table | Acres | SF | SFA/TH | MF | SF | SFA/TH | MF | SF | SFA/TH | MF | SF | SFA/TH | MF | SF | SFA/TH | MF | SF | SFA/TH | MF | SF | SFA/TH | MF | SF | SFA/TH | MF | SF | SFA/TH | MF | SF | SFA/TH | MF | SF | SFA/TH | MF
North Ridge - Oakwood |  |  | 200 | [5 empty] | 50 |  |  | 50 |  |  | 50 |  |  | 50
Keto-Maplewood PUD | 275 | 950 | [8 empty] | 50 |  |  | 70 |  |  | 70 |  |  | 70 |  |  | 70 |  |  | 70 |  |  | 70 |  |  | 70
TRR 12 | 28 | 164 | [5 empty] | 40 |  |  | 40 |  |  | 40 |  |  | 44
Replat of Lot 44 Country Acres 9 | .317 Acres | 9 |  |  | 3 |  |  | 3 |  |  | 3
TRR 13 | 81.362 | 254 | [5 empty] | 20 |  |  | 50 |  |  | 50 |  |  | 50 |  |  | 50 |  |  | 34
Revere (Great Plains Village) Filing 1 | 73.578 | 170 | 150 |  |  |  |  | 20 |  |  | 50 | 50 |  | 50 | 50 |  | 50 | 40 |  |  |  |  | 70
TRR 8 |  | 47 | [5 empty] | 20 |  |  | 7
Ridge 1 |  | 208 | [5 empty] | 40 |  |  | 60 |  |  | 60 |  |  | 48
Ridge 2 |  | 81 | [5 empty] | 51 |  |  | 30
Ridge 3 (SFA?) |  | ?
Mallard Ridge / J Village | 90 | 263 |  |  | 40 |  |  | 60 |  |  | 60 |  |  | 60
Mallard Ridge MF | 12 |  |  | 150 | [5 empty] | 75 |  |  | 75
TRR 7 |  | 81 |  |  | 40 |  |  | 41
TRR 10 | 10 | 35 |  |  | 30 |  |  | 5
Johnstown Farms F3 |  | 241 | [5 empty] | 50 |  |  | 50 |  |  | 50 |  |  | 50 |  |  | 41
Leftover lots |  | 60 |  |  | 10 |  |  | 10 |  |  | 10 |  |  | 10 |  |  | 10 |  |  | 10
Great Plains Village |  | 1150 |  | 500 | [6 empty] | 70 |  |  | 70 |  | 100 | 70 |  | 100 | 70 |  | 100 | 70 |  | 100 | 70 |  | 100 | 70 |  |  | 70
Mountain View West |  |  | 420 |  |  | 50 |  |  | 50 |  |  | 50 |  |  | 50 |  |  | 50 |  |  | 50 |  |  | 50 |  |  | 50 |  |  | 20
Pending/ unknown
Podtburg |  | 988
Purvis |  | 200 | 100
Welty
TRR 14